## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
RACI Matrix
| Table 1 | RACI Matrix
Role Template
| Table 1 | Role Template

## RACI Matrix
RACI Matrix Chart
| Person 1 | Person 2 | Person 3 | Person 4 | Person 5 | Person 6 | Person 7 | Person 8 | Person 9 | Person 10
Vision, Goals, and Backlog (EXAMPLE) | A | C | R | I | I | R | C | C | I | I
Legend
R = Responsible - "The doer" | A: The person who is working on this and responsible for implementation.
A = Accountable - "The buck stops here" | A: The person who makes the final decision and has the ultimate ownership.
C = Collaborates - "In the loop" | A: The person who is impacted and must be consulted before a decision or action is taken.
I = Informed - "Keep in the picure" | A: The person who should be informed that a decision or action has been taken.
Horizontal Analysis
Lots of R's | A: Too many people involved.
No R's or A's | A: Who does it?
More than 1 A | A: Confusion
Lots of C's and I's | A: DO they all need to know?
Vertical Analysis
Lots of R's | A: Too much work
No empty space | A: Too much work
No R's or A's | A: Can function/role be eliminated?
Too many A's | A: Is accountability at the right level
Roles
Activity / Area

## Role Template
Role Name | Product Owner
Role Purpose / Summary | The product owner is the voice of the customer, represents the internal stakeholders, and is responsible for delivering the highest possible value to the business.
Duties And Responsibilities
Clearly expressing Product Backlog items.
Available and Engaged
Alignment on Vision
Participation in Development Events
Ordering the items in the Product Backlog to best achieve goals and missions.
Empowered
Ensuring that the Product Backlog is visible, transparent, and clear to all, and shows what the Scrum Team will work on next.
Actively supports the business with progress updates and metrics
Ensuring the Development Team understands items in the Product Backlog to the level needed.
Accountable | Optimizing the value of the work the Development Team performs.
Required Competencies | Great Communication, Value Analysis, Relationship Building, Influencing Skills, Leadership, Decision Making, Planning, User Research, Collaboration, Prototyping, Lean and Agile approaches.